## Slide 1
PROJECT DELIVERY PLAN · 2025
ANM Community App
Milestone & Implementation Plan
A precise execution framework for delivering a .NET 8 + Ionic/Capacitor + PostgreSQL community platform in 10 weeks.
PROJECT
ANM Community App
DURATION
10 Weeks + 30-Day Hypercare
METHODOLOGY
Agile / 2-Week Sprints
FRAMEWORK
.NET 8 + PostgreSQL
VERSION
v1.0 — Draft
ANM Community App — Milestone & Implementation Plan · Confidential

## Slide 2
DELIVERY SCORECARD
At a Glance — Key Delivery Numbers
5
Delivery Phases
Discovery → Deployment → Hypercare
20
Key Milestones
3 Formal Sign-off Gates
5
Agile Sprints
2 Weeks Each
130+
Story Points
Across All 5 Sprints
10
Weeks to Go-Live
App Store + Play Store
35+
Checklist Items
Pre-Launch Verification

## Slide 3
TIMELINE
Project Gantt — 10-Week + Hypercare Overview
Activity
Wk 1
Wk 2
Wk 3
Wk 4
Wk 5
Wk 6
Wk 7
Wk 8
Wk 9
Wk 10
HC-1
HC-2
Phase 1: Discovery & Config
1–2
1–2
Stakeholder Workshops
Wk 1
DB Schema + API Contract
1–2
1–2
Figma Design Sign-off
Wk 2
Phase 2: Core Customisation
3–6
3–6
3–6
3–6
Auth + Member Directory
3–4
3–4
Prayer Requests + Video
4–6
4–6
4–6
Backend APIs (.NET 8)
3–6
3–6
3–6
3–6
Phase 3: Feature Completion
7–8
7–8
Messaging + VoIP + FCM
7–8
7–8
Phase 4: QA, UAT & Launch
9–10
9–10
xUnit + Playwright + Appium
Wk 9
UAT + App Store Submit
Wk 10
Hypercare (Free — 30 Days)
HC
HC
🚀 Go-Live: End of Week 10 | 🏁 Framework pre-built modules save 4–6 weeks vs greenfield build | HC = Hypercare (30-day free support)

## Slide 4
MILESTONE REGISTER
Milestone Register — All 20 Milestones
ID
Week
Milestone
Gate
M01
Wk 1
Kickoff & Stakeholder Workshop Complete
Sign-off
M02
Wk 1
Development Environment + CI/CD Pipeline Live
Team
M03
Wk 2
PostgreSQL Schema + API Contract Approved
Sign-off
M04
Wk 2
Figma High-Fidelity Designs Signed Off
Sign-off
M05
Wk 3
Firebase Auth + Onboarding Flow Complete
Demo
M06
Wk 4
Member Directory + Detail Page Done
Demo
M07
Wk 5
Member History Notes Feature Complete
Demo
M08
Wk 5
Prayer Requests Module Deployed
Demo
M09
Wk 6
Video Library + CloudFront CDN Streaming Live
Demo
M10
Wk 6
All Core APIs (.NET 8) Feature-Complete
Sign-off
M11
Wk 7
Twilio Chat + VoIP Calling Integrated
Demo
M12
Wk 8
Push Notifications (FCM) Live on Device
Demo
M13
Wk 8
Admin RBAC + Deep-Link Polish Complete
Demo
M14
Wk 9
xUnit + Playwright + Appium Tests Complete
QA Gate
M15
Wk 9
OWASP Security Audit Passed
Sign-off
M16
Wk 9
Production AWS Infrastructure Live
DevOps
M17
Wk 10
UAT Sign-off by ANM Stakeholders
Sign-off
M18
Wk 10
Performance Tests — p95 < 200ms Confirmed
QA Gate
M19
Wk 10
App Store + Play Store Submissions
DevOps
M20
Wk 10
🚀 Go-Live — ANM Community App is Live
Go-Live

## Slide 5
GOVERNANCE
Formal Sign-Off Gates
3 mandatory gates before proceeding — ensures ANM leadership controls every major transition.
Gate G1
End Wk 2
Design & Architecture Sign-Off
✅ PostgreSQL schema reviewed by ANM team
✅ 14 REST API endpoints documented & agreed
✅ Figma UI designs approved (brand, fonts, colours)
✅ CI/CD pipeline verified with sample build
✅ Development environment access confirmed
⚠ No development begins until designs & schema are signed off.
Gate G2
End Wk 6
MVP Core Feature Sign-Off
✅ Auth + Member Directory demo accepted
✅ Prayer Requests flow verified end-to-end
✅ Video streaming via CloudFront <2s confirmed
✅ Member History notes live in staging
✅ All core APIs (.NET 8) feature-complete
⚠ Phase 3 features only begin once core is approved.
Gate G3
End Wk 10
UAT & Go-Live Sign-Off
✅ All 35+ pre-launch checklist items checked
✅ OWASP security audit passed & documented
✅ xUnit + Playwright + Appium test report attached
✅ ANM UAT participants sign acceptance form
✅ App Store / Play Store submissions approved
⚠ Production release requires written stakeholder sign-off.

## Slide 6
PHASE BREAKDOWN
Phase-by-Phase Task Breakdown
Phase 01: Discovery & Framework Config
Wk 1–2
Stakeholder requirements workshop
ANM brand config + theming in Ionic
PostgreSQL schema design (EF Core 8 migrations)
REST API contract (14 endpoints, OpenAPI spec)
CI/CD pipeline — GitHub Actions + AWS ECS
Figma UI design + sign-off gate G1
Phase 02: Core Customisation
Wk 3–6
Firebase Auth + biometric onboarding
Member Directory + Detail (React + Ionic)
Member History (pastoral notes — EF Core 8)
Prayer Requests module + pray interactions
Video Library + AWS S3 + CloudFront streaming
Backend .NET 8 APIs (all 4 core modules) — G2
Phase 03: Feature Completion
Wk 7–8
Twilio Chat (1:1 in-app messaging)
Twilio VoIP (in-app calling)
Push notifications (Firebase FCM)
Admin backend endpoints (RBAC .NET 8)
Deep-link routing (Ionic Router)
Performance audit + image optimisation
Phase 04: QA, UAT & Launch
Wk 9–10
xUnit unit tests (80%+ coverage)
Testcontainers API integration tests
Playwright E2E — web flows
Appium E2E — iOS Simulator + Android
OWASP mobile security audit
UAT with ANM team → App Store submit
Phase 05: Hypercare
30 Days Free
30-day free post-launch support
Performance monitoring (CloudWatch)
Critical bug fixes at no charge
Admin team training & handover
Source code + doc delivery
Phase 2 backlog planning

## Slide 7
SPRINT PLANNING
Sprint 1 — Weeks 1–2: Discovery & Framework Config
Goal: Establish all foundations before a single line of feature code is written. Sign-off Gate 1 at end of Week 2.
SP
Story
Owner / Notes
8pt
Project kickoff + requirements finalisation
PM + Architect | ANM team workshop, scope signed
5pt
PostgreSQL schema + API contract doc (OpenAPI)
Backend + Architect | 5 tables, 14 endpoints (EF Core 8)
8pt
CI/CD pipeline — GitHub Actions + ECS + Docker
DevOps | PR gates → .NET 8 build → deploy to staging
5pt
AWS RDS PostgreSQL provisioning (staging)
DevOps | RDS Multi-AZ config, security group, VPC
8pt
Ionic/Capacitor project scaffold + brand theming
Mobile Dev | ANM colours, fonts, bottom nav, dark mode
8pt
Figma high-fidelity UI designs — all screens
UI/UX | 9 screens, component library, design sign-off
3pt
Firebase Auth project setup + .NET JWT middleware
Backend | Firebase Admin SDK, JWT Bearer, role claims
3pt
Security Consultant kickoff brief
Security | OWASP checklist, pentest plan, data mapping
Sprint 1 Total: 48 Story Points | End Gate: Design & Architecture Sign-Off | Sprint Review: EOD Wk 2 Demo

## Slide 8
SPRINT PLANNING
Sprint 2 — Weeks 3–4: Core Customisation Part 1
Goal: Auth, Member Directory, History & core APIs live in staging by end of Week 4.
SP
Story
Owner / Notes
6pt
Firebase Auth + biometric onboarding (Capacitor Biometric)
Mobile Dev | Login, OTP, Google OAuth, fingerprint
8pt
Member Directory — search, filter, role badges (Ionic list)
Mobile Dev | Paginated, debounced search, avatars
5pt
Member Detail page — call/message/pray CTAs
Mobile Dev | Profile card, stat chips, action buttons
5pt
Member History (pastoral notes) — CRUD + timestamp log
Full Stack | .NET 8 API + EF Core + Ionic UI
5pt
.NET 8 REST APIs (auth + directory + history modules)
Backend | EF Core 8 migrations, JWT auth, xUnit tests
3pt
AWS RDS PostgreSQL staging provisioned
DevOps | RDS Multi-AZ, security group, VPC config
3pt
GitHub Actions CI/CD — PR gate + staging auto-deploy
DevOps | Docker build → ECS Fargate staging
3pt
Weekly demo prep + stakeholder review
PM | Demo recording + feedback log
Sprint 2 Total: 38 Story Points | Checkpoint: Auth + Directory Live in Staging | Sprint Review: EOD Wk 4 Demo

## Slide 9
SPRINT PLANNING
Sprint 3 — Weeks 5–6: Core Customisation Part 2
Goal: Prayer Requests, Video Library, admin APIs complete. Sign-off Gate 2 (MVP Core) at end of Week 6.
SP
Story
Owner / Notes
8pt
Prayer Requests — submit, browse, pray, anonymous flag
Full Stack | JWT-auth .NET 8 API + real-time count
6pt
Video Library — category feed + CloudFront presigned stream
Full Stack | S3 upload pipeline + CDN streaming <2s
5pt
.NET 8 REST APIs for prayer + video modules
Backend | EF Core 8, xUnit tested, OpenAPI documented
4pt
Admin RBAC — role-based access on all .NET 8 endpoints
Backend | [Authorize(Roles)] + policy middleware
4pt
Deep-link routing + bottom-nav polish (Ionic Router)
Mobile Dev | Universal links, gestures, transitions
4pt
Performance audit + image lazy-loading optimisation
Mobile Dev + QA | Lighthouse + Capacitor perf profiling
3pt
Weekly demo prep + stakeholder review
PM | Demo recording + feedback log
3pt
Gate 2 MVP Core sign-off session
PM + Architect | Wk 6 formal review + sign-off form
Sprint 3 Total: 37 Story Points | End Gate G2: MVP Core Sign-Off | Sprint Review: EOD Wk 6 Demo

## Slide 10
SPRINT PLANNING
Sprint 4 — Weeks 7–8: Feature Completion
Goal: Twilio Chat + VoIP, FCM push notifications, and all advanced features live in staging.
SP
Story
Owner / Notes
6pt
Twilio Chat integration (1:1 messaging, read receipts)
Mobile+Backend | Twilio Conversations SDK + .NET 8
6pt
Twilio VoIP integration (in-app calling, no phone sharing)
Mobile+Backend | Twilio Voice + Capacitor audio
4pt
Firebase FCM push notifications (iOS + Android)
Mobile+DevOps | Topic targeting + delivery history log
5pt
Group Chat / Forum threads (Ionic + SignalR WebSocket)
Full Stack | .NET 8 SignalR hub + Ionic real-time UI
4pt
Event Calendar + RSVP module
Full Stack | .NET 8 + EF Core + Ionic calendar view
4pt
Admin dashboard — user management, content moderation
Full Stack | RBAC admin panel, reporting views
3pt
Performance audit — API p95 < 200ms target
DevOps + QA | k6 load test 200 concurrent users
3pt
Weekly demo prep + stakeholder review
PM | Demo recording + feedback log
Sprint 4 Total: 35 Story Points | Checkpoint: All Features Feature-Complete in Staging | Sprint Review: EOD Wk 8 Demo

## Slide 11
SPRINT PLANNING
Sprint 5 — Weeks 9–10: QA, UAT & Go-Live
Goal: Full test suite complete, security passed, UAT signed off, apps live on App Store and Play Store. 🚀
SP
Story
Owner / Notes
4pt
xUnit unit tests — 80%+ coverage on all .NET 8 services
Wk9 · QA | Mocked services, edge cases, all modules
4pt
Testcontainers API integration tests — all endpoints
Wk9 · QA | Dockerised PostgreSQL test DB, +/- paths
4pt
Playwright E2E — web flows (member, prayer, video, chat)
Wk9 · QA | Headed + headless CI runs, all journeys
4pt
Appium E2E — iOS Simulator + Android Emulator
Wk9 · QA | Login → member → pray → video → VoIP call
3pt
OWASP security audit + penetration test
Wk9 · Security | Mobile Top 10, JWT review, RDS audit
3pt
Production infrastructure (RDS Multi-AZ, ECS Fargate, WAF)
Wk9 · DevOps | Prod deploy, CloudWatch alarms, scaling
3pt
k6 load test — 500 concurrent users, p95 < 200ms
Wk10 · QA + DevOps | Full load test report
3pt
UAT with ANM team (20 pilot members) + sign-off form
Wk10 · PM | Acceptance testing, issue triage, sign-off
3pt
App Store + Play Store submission + metadata
Wk10 · DevOps | Capacitor builds, screenshots, review
2pt
Source code handover + deployment docs delivered
Wk10 · PM + Architect | Repo access, runbooks, wiki
Sprint 5 Total: 33 Story Points | End Gate G3: UAT & Go-Live Sign-Off | 🚀 App Store + Play Store Live — Week 10

## Slide 12
TEAM STRUCTURE
Team Structure & RACI
Activity
PM
ARC
DES
MOB ×2
BAK
DEV
QA
SEC
Discovery & Stakeholder Workshops
A
R
C
I
I
I
I
I
DB Schema + API Contract
A
R
I
C
R
C
C
C
Figma UI/UX Design
A
C
R
C
I
I
I
I
CI/CD + AWS Infrastructure
A
I
I
I
C
R
C
I
React + Ionic Mobile Development
A
C
C
R
I
I
I
I
ASP.NET Core .NET 8 Backend APIs
A
C
I
I
R
C
C
C
xUnit + Playwright + Appium QA
A
C
I
C
C
I
R
C
OWASP Security Audit
A
C
I
I
I
I
C
R
App Store / Play Store Submission
A
I
I
R
I
C
C
I
Hypercare & Handover
R
C
I
C
C
C
C
I
R = Responsible A = Accountable C = Consulted I = Informed
MOB=Mobile Dev BAK=Backend Dev DEV=DevOps ARC=Architect DES=Designer SEC=Security

## Slide 13
QUALITY ASSURANCE
QA & Testing Strategy
Unit Tests
xUnit (.NET 8)
👤 Backend Dev + QA · 📅 Every PR
All ASP.NET Core service-layer business logic tested in isolation. Mocked dependencies via NSubstitute. 80%+ line coverage enforced in CI gate.
Integration Tests
xUnit + Testcontainers
👤 QA · 📅 Wk 6
All 14 REST API endpoints tested against a real Dockerised PostgreSQL database. Positive + negative paths. Auth header validation. Response schema verified.
E2E — Web
Playwright
👤 QA · 📅 Wk 6
Full user journeys in Chromium/Firefox/WebKit: login → member search → prayer request → video play. Runs headed in dev, headless in CI.
E2E — Mobile
Appium
👤 QA · 📅 Wk 6
iOS Simulator (iPhone 15 Pro) + Android Emulator (Pixel 7). Flows: login, member directory, prayer, video stream, Twilio call. Real Capacitor native APIs tested.
Performance
k6
👤 DevOps + QA · 📅 Wk 6
500 concurrent users. API response p95 < 200ms target. Video CloudFront initial load < 2s. RDS connection pool saturation tested at 1,000 VUs.
Security
OWASP + Pentest
👤 Security Consultant · 📅 Wk 6
OWASP Mobile Top 10 audit. JWT expiry + rotation verified. SQL injection impossible (EF Core parameterised queries). S3 bucket policies audited. Penetration test report delivered.

## Slide 14
GO-LIVE READINESS
Infrastructure & Pre-Launch Checklist
⚙️ Infrastructure Setup (Week 9)
◦ AWS RDS PostgreSQL 16 Multi-AZ cluster provisioned in prod region
◦ RDS security group: ECS task CIDR only (no public endpoint)
◦ ECS Fargate task definition: .NET 8 container, 2 vCPU / 4GB RAM
◦ Auto-scaling policy: target CPU 70%, min 1 task, max 10 tasks
◦ CloudWatch alarms: CPU >80%, error rate >1%, p99 latency >500ms
◦ AWS S3 bucket — private + CloudFront distribution with signed URLs
◦ SSL certificate (ACM) + custom domain configured on ALB
◦ GitHub Actions CI/CD pipeline: PR → build → test → ECS deploy
◦ Firebase Auth production project — production app credentials
◦ Twilio production account — voice + SMS phone numbers activated
◦ Firebase FCM production credentials + iOS APNs certificate
◦ ECS task IAM role: S3 read/write, SSM Parameter Store, CloudWatch
◦ AWS WAF rules on ALB — rate limiting 1,000 req/min per IP
◦ Secrets in AWS SSM Parameter Store (no env vars in code)
✅ Pre-Launch Checklist (35+ items)
✅ All 14 REST API endpoints return expected responses
✅ Playwright E2E suite passes in headless CI (100% pass rate)
✅ Appium E2E passes on iOS Simulator + Android Emulator
✅ Video streaming: first frame < 2s via CloudFront CDN
✅ Push notification delivered in < 5s on physical device
✅ Twilio VoIP call connects in < 3s (staging → prod)
✅ JWT token expiry + refresh flow verified
✅ PostgreSQL RDS failover tested (Multi-AZ switchover)
✅ OWASP Mobile Top 10 — zero critical findings
✅ Privacy policy + terms accepted at onboarding
✅ App Store screenshots + metadata approved
✅ Play Store listing + content rating submitted
✅ ANM UAT participants — acceptance form signed
✅ DNS/domain records propagated globally
✅ Rollback procedure documented and tested
✅ Admin team trained on backend portal
✅ Source code + deploy docs delivered to ANM

## Slide 15
COMMUNICATION
Communication & Reporting Plan
Daily
Standup
Slack / Teams
👥 Dev Team
15-min async standup: yesterday / today / blockers. PM reviews blockers and escalates within 2 hours.
Weekly
Demo + Update
Video Call + Deck
👥 ANM Stakeholders
30-min live demo of features built that week. Risk update. Next week preview. Recorded and shared.
End of Sprint
Sign-Off Review
Video Call
👥 ANM Leadership
Formal walkthrough of deliverables vs sprint goal. Sign-off form issued. Decisions documented.
Ad-Hoc
Escalations
WhatsApp / Email
👥 PM ↔ ANM Lead
Critical blockers, scope change requests, and timeline impacts communicated within 1 hour of discovery.
📝 All decisions and scope changes require written confirmation. No verbal approvals accepted for scope or timeline changes.

## Slide 16
CHANGE MANAGEMENT
Change Request & Scope Management
Scope changes after Week 2 sign-off require a formal Change Request. This protects both ANM and the delivery team from scope creep.
01
Request Raised
👤 ANM Lead
ANM raises request via email or Slack to PM with description of change and business justification.
→
02
Impact Analysis
👤 PM + Architect
PM and Architect assess timeline impact, cost delta, and technical effort within 48 hours.
→
03
CR Document
👤 PM
PM issues formal CR document: change description, effort, cost impact, revised timeline.
→
04
ANM Approval
👤 ANM Lead
ANM Lead signs CR document. No work begins until written approval is received.
→
05
Sprint Backlog Update
👤 PM + Team
CR is added to next sprint or Phase 2 backlog. Timeline adjusted accordingly.
🔒 Locked Scope
Weeks 1–10 scope is locked after Gate 1 sign-off. New requests go to Phase 2.
⏱️ 48h Response
All CRs acknowledged within 48 hours with preliminary impact statement.
📋 Backlog First
All non-critical CRs added to Phase 2 backlog to preserve 10-week commitment.

## Slide 17
10 Weeks. Framework-Accelerated. Yours.
Built on Proprietary .NET 8 + PostgreSQL + Ionic/Capacitor Framework
This plan represents our commitment to deliver ANM's community platform with precision, transparency, and zero scope surprises. Every milestone is tracked, every gate is signed off, and every line of code belongs to ANM on day one.
20
Milestones Tracked
130+
Story Points Planned
35+
Go-Live Checklist Items
10 Wks
To App Store Launch
📅 Schedule Discovery Call
30 mins with ANM leadership
✍️ Sign & Kickoff
30% deposit starts Week 1
💬 Ask Any Question
hello@yourstudio.com
ANM Community App — Milestone & Implementation Plan · Powered by Proprietary .NET 8 Framework · Confidential