TECHNICAL FEASIBILITY STUDY ANM Community App Proprietary .NET 8 Enterprise Framework STACK ASP.NET Core .NET 8 + Ionic 7; DATABASE PostgreSQL 16 on AWS RDS; DELIVERY 10 Weeks + 30-Day HC; VERSION v1.0 ¦ June 2025.

# 1. Executive Summary

This document presents a comprehensive technical feasibility study for the ANM Community App — a native iOS, Android, and web community platform for Assemblies of Nagaland Ministries. The study evaluates the selected technology stack across six dimensions: technical viability, team capability, infrastructure readiness, timeline feasibility, cost sustainability, and risk profile.

VERDICT: FULLY FEASIBLE All selected technologies are production-proven, actively maintained, and well-supported. The proprietary .NET 8 enterprise framework provides a significant head-start, reducing delivery risk and accelerating the 10-week timeline vs. an estimated 14–16 weeks for a greenfield build. No blocking technical risks identified. Three medium risks flagged with clear mitigations.

The proposed stack — ASP.NET Core .NET 8, React + Ionic/Capacitor 7, and PostgreSQL 16 on AWS RDS — represents an enterprise-grade combination that is battle-tested at scale across banking, healthcare, and community platforms globally. All individual components are MIT or Apache-2 licensed (or commercially backed with SLA), ensuring no licensing risk for ANM.

# 2. Project Overview

## 2.1  Application Scope

The ANM Community App is a multi-platform community engagement application delivering the following functional domains:

- Member Directory — searchable, filterable member roster with detail pages and pastoral notes

- Prayer Requests — anonymous/named prayer submission, browse, and pray interactions

- Video Library — categorized sermon/content library with CloudFront CDN streaming

- In-App Messaging — 1:1 chat via Twilio Conversations SDK

- VoIP Calling — in-app voice calls via Twilio Voice (no phone number sharing)

- Push Notifications — Firebase FCM for iOS and Android

- Admin Backend — role-based admin portal for content and user management

- Real-time features — SignalR WebSocket for live prayer counts and notifications

## 2.2  Finalized Technology Stack

| Layer | Technology | Version / Details |
| --- | --- | --- |
| Frontend / Mobile | React + Vite + Ionic / Capacitor | Ionic 7, Capacitor 7 — iOS 16+, Android 12+, Web (PWA) |
| Backend API | ASP.NET Core | .NET 8 LTS (C#) — OpenAPI, Middleware, DI, Health Checks |
| ORM / Database | EF Core + PostgreSQL | EF Core 8 + Npgsql + PostgreSQL 16 on AWS RDS |
| Authentication | Firebase Auth + JWT | Firebase Auth v9 SDK + JWT Bearer (.NET 8 middleware) |
| Real-time | SignalR | .NET 8 SignalR — WebSocket hub for live features |
| Messaging / VoIP | Twilio | Twilio Conversations (chat), Voice SDK (VoIP), SMS (OTP) |
| Storage + CDN | AWS S3 + CloudFront | Private S3 bucket + signed CloudFront URLs |
| Push Notifications | Firebase FCM | Firebase Cloud Messaging — topic + device targeting |
| Testing (Unit) | xUnit + NSubstitute | xUnit 2.x, Testcontainers for Dockerised PostgreSQL tests |
| Testing (E2E) | Playwright + Appium | Playwright (web), Appium 2.x (iOS Simulator + Android) |
| Security | OWASP + AWS WAF | OWASP Mobile Top 10, JWT rotation, WAF rate limiting |
| CI/CD | GitHub Actions + ECS | PR gates → .NET 8 build → Docker → ECS Fargate deploy |
| Infrastructure | AWS ECS Fargate | Serverless containers; RDS Multi-AZ, CloudWatch, ALB |

# 3. Component-by-Component Feasibility

## 3.1  Frontend / Mobile — React + Ionic/Capacitor 7

Ionic/Capacitor 7 is a web-native mobile framework that compiles a React/TypeScript web app into native iOS and Android binaries using Capacitor's native bridge. This enables a single codebase to deploy to iOS, Android, and the web simultaneously.

Feasibility: HIGH Ionic 7 + Capacitor 7 is actively developed by Ionic Inc. (Series B funded). Used in production by NASA, GE Healthcare, and Burger King. All required Capacitor plugins (Biometric, Camera, Push, VoIP) are available and maintained.

| ✅ PROS |  | ❌ CONS |
| --- | --- | --- |
| Single codebase for iOS, Android, and Web (PWA) — eliminates 3 separate codebases |  | Performance ceiling below fully native Swift/Kotlin for GPU-intensive apps (not applicable here) |
| Uses standard React/HTML/CSS skills — broad talent pool for future team growth |  | Capacitor plugin ecosystem smaller than React Native for some edge-case hardware features |
| Capacitor 7 provides first-class access to native APIs (Biometrics, Camera, NFC, Notifications) |  | WebView rendering subtle differences from native UI components (mitigated by Ionic's themed components) |
| Ionic component library optimized for touch — professional UX out of the box |  | App bundle size larger than pure native apps (~15–25 MB vs. ~8 MB native) |
| Hot reload during development dramatically speeds up iteration |  | Twilio VoIP requires Capacitor community plugin — additional integration testing needed |
| Web version deployable as PWA — accessible on any browser without App Store download |  |  |
| Strong TypeScript support — catches bugs at compile time, not production |  |  |

## 3.2  Backend API — ASP.NET Core .NET 8

ASP.NET Core .NET 8 is Microsoft's Long-Term Support (LTS) runtime for server-side applications. It delivers high-performance REST APIs, built-in dependency injection, OpenAPI (Swagger) integration, SignalR for real-time communication, and enterprise-grade middleware.

Feasibility: HIGH .NET 8 LTS is supported until November 2026. TechEmpower benchmarks rank ASP.NET Core in the top 5 fastest API frameworks globally. Used by StackOverflow, Azure, and thousands of enterprise applications.

| ✅ PROS |  | ❌ CONS |
| --- | --- | --- |
| TechEmpower Benchmark Top 5: ASP.NET Core outperforms Node.js/Express by 3–5x in throughput |  | C# / .NET skills less common in pure startup market vs. Node.js developers |
| Long-Term Support (LTS) until November 2026 — guaranteed security patches |  | Cold start time for ECS containers slightly higher than Lambda (mitigated with min-task=1 config) |
| Built-in DI container, middleware pipeline, health checks, and OpenAPI — no extra packages needed |  | License requirement: .NET 8 runtime is MIT open-source — zero cost; no commercial license needed |
| EF Core 8 ORM provides type-safe database access with automatic migration management |  | Verbosity: C# is more verbose than Python/Node for simple scripts (not relevant for production APIs) |
| SignalR built-in for WebSocket real-time features — no additional runtime or library |  |  |
| C# strong typing prevents entire categories of runtime bugs that TypeScript cannot catch |  |  |
| Microsoft-backed enterprise adoption — banks, hospitals, and government systems run on .NET 8 |  |  |
| Docker + ECS Fargate containerization is first-class — minimal devops friction |  |  |

## 3.3  Database — PostgreSQL 16 on AWS RDS

PostgreSQL 16 is the world's most advanced open-source relational database. On AWS RDS, it runs as a managed service — automated backups, failover, patching, and monitoring without manual DBA overhead.

Feasibility: HIGH PostgreSQL is the #1 most admired database in Stack Overflow Developer Survey 2023 & 2024. AWS RDS PostgreSQL is AWS's second most-used managed database product. Netflix, Instagram, and Shopify use PostgreSQL at scale.

| ✅ PROS |  | ❌ CONS |
| --- | --- | --- |
| ACID compliant — transactions guaranteed; no data loss on node failure |  | Vertical scaling required before horizontal sharding — requires db.t4g.xlarge beyond ~10,000 concurrent users |
| JSON + JSONB support for semi-structured data without sacrificing relational integrity |  | Cost: db.t4g.medium (~₹18,500/mo) is higher than self-managed PostgreSQL on EC2 (~₹6,000/mo) |
| Full-text search built-in — no Elasticsearch needed for member directory search |  | Schema migrations must be managed carefully — EF Core migrations need review before production deploy |
| Row-level security (RLS) for multi-tenant data isolation — critical for community platforms |  | Connection pooling (PgBouncer) recommended at >500 concurrent API connections — adds one component |
| AWS RDS Multi-AZ: automatic failover in <60 seconds — 99.95% availability SLA |  |  |
| Automated backups, point-in-time recovery to any second in last 35 days |  |  |
| EF Core 8 + Npgsql provides full LINQ-to-SQL with compiled query caching |  |  |
| PostGIS extension available if location features added in Phase 2 |  |  |

## 3.4  Authentication — Firebase Auth + JWT Bearer

Firebase Authentication handles user identity (Google OAuth, email/password, OTP via SMS) and issues signed JWT tokens. The .NET 8 backend validates these tokens via the Firebase Admin SDK's JWT Bearer middleware.

Feasibility: HIGH Firebase Auth is used by 3 million+ apps globally. The .NET Firebase Admin SDK is officially maintained by Google. The JWT validation approach is industry-standard and requires no additional infrastructure.

| ✅ PROS |  | ❌ CONS |
| --- | --- | --- |
| Zero infrastructure to manage — Google handles identity servers, rate limiting, and uptime |  | Dependency on Google infrastructure — Firebase outages (rare, <0.01% annually) affect auth |
| Built-in OTP/SMS verification — eliminates custom OTP logic |  | Firebase project locked to Google Cloud — migration to self-hosted auth is significant effort |
| Google and Apple OAuth flows supported out of the box |  | Phone number verification via SMS costs ~₹4.9/SMS beyond free tier |
| JWT tokens stateless — backend validates without database lookups on every request |  | Custom auth claims (roles) must be set via Admin SDK — adds one API call per role assignment |
| 10,000 users/month free — scales commercially at low cost beyond that |  |  |
| Biometric authentication delegates to device (no biometric data stored in server) |  |  |
| Token refresh handled automatically by Firebase SDK |  |  |

## 3.5  Communications — Twilio (Chat + VoIP + SMS)

Twilio provides three communication channels: Conversations SDK for in-app messaging, Twilio Voice for VoIP calling (no phone numbers exchanged between users), and SMS for OTP and system notifications.

Feasibility: HIGH Twilio powers communications for Airbnb, Uber, WhatsApp Business, and 290,000+ businesses. Twilio Conversations and Voice SDKs are available as Capacitor-compatible packages for iOS and Android.

| ✅ PROS |  | ❌ CONS |
| --- | --- | --- |
| No phone numbers shared between users — VoIP calls stay in-app (privacy-first) |  | Usage-based pricing: costs scale with call minutes and message volume (~₹4,825/mo estimated) |
| Twilio Conversations handles message persistence, read receipts, and typing indicators automatically |  | Twilio Voice requires Capacitor community plugin — not officially maintained by Twilio |
| Global infrastructure: <150ms call connection latency in India |  | Network quality affects VoIP call quality — requires graceful degradation UX |
| SDK available for React/Ionic and .NET — single vendor for chat + voice + SMS |  | India regulatory compliance for SMS: DLT registration required for transactional SMS (1–2 week process) |
| Compliance: HIPAA-eligible, GDPR-ready, ISO 27001 certified |  | Twilio outages (rare) affect in-app calling — fallback to phone calling recommended as backup |
| Webhook-based event delivery to .NET 8 backend — no polling required |  |  |
| Programmable — custom logic for message filtering, moderation, and escalation |  |  |

## 3.6  Infrastructure — AWS ECS Fargate + RDS + S3 + CloudFront

The entire backend infrastructure runs on AWS managed services — ECS Fargate for serverless .NET 8 containers, RDS PostgreSQL 16 for managed database, S3 for media storage, and CloudFront CDN for global video delivery.

Feasibility: HIGH AWS is the world's largest cloud platform with 99.99% compute SLA. ECS Fargate eliminates EC2 management overhead. CloudFront's 450+ PoPs ensure <100ms latency for video delivery across India.

| ✅ PROS |  | ❌ CONS |
| --- | --- | --- |
| ECS Fargate: zero server management — AWS handles OS patching, scaling, and container placement |  | Monthly cost ~₹44,825 (AWS + Twilio) is client-borne operating expense — must be budgeted |
| Auto-scaling: ECS scales .NET 8 containers 1–10 tasks based on CPU threshold — handles traffic spikes |  | AWS vendor lock-in: migrating to Azure/GCP later requires re-engineering CI/CD and some services |
| RDS Multi-AZ: automatic failover in <60 seconds — no manual intervention during node failure |  | ECS cold start: first request after scale-to-zero ~2–3 seconds (mitigated with min 1 task always running) |
| CloudFront CDN: 450+ edge locations globally — sub-2-second video load time from India |  | CloudFront egress costs scale with video consumption — unexpected viral content could spike costs |
| AWS WAF: rate limiting + bot protection without custom firewall code |  | Multi-region setup not included in base plan — DR scenario requires additional configuration |
| GitHub Actions + ECS deploy pipeline: PR → build → test → deploy in ~8 minutes |  |  |
| CloudWatch: centralized logging, metrics, and alerts — no separate monitoring infrastructure |  |  |
| SSM Parameter Store: secrets management at zero cost — no HashiCorp Vault needed |  |  |

# 4. Alternatives Considered & Rejected

The following table documents the alternative technologies evaluated for each layer and the rationale for the chosen approach.

| Layer | Chosen | Alt 1 | Alt 2 | Why Chosen |
| --- | --- | --- | --- | --- |
|  | ✅ 0 |  |  |  |
|  | ✅ 1 |  |  |  |
|  | ✅ 2 |  |  |  |
|  | ✅ 3 |  |  |  |
|  | ✅ 4 |  |  |  |
|  | ✅ 5 |  |  |  |
|  | ✅ 6 |  |  |  |
|  | ✅ 7 |  |  |  |
|  | ✅ 8 |  |  |  |

# 5. Risk Assessment

The following risks were identified during feasibility analysis. No showstopper risks were found. All risks have documented mitigations.

| Risk | Impact | Prob. | Mitigation |
| --- | --- | --- | --- |
| Twilio VoIP Capacitor Plugin Instability | Medium | Low | Plugin is community-maintained. Mitigated by integration testing in Sprint 4 (Wk 7–8) with fallback to standard phone call if VoIP fails. Twilio also has official React Native SDK as reference. |
| RDS PostgreSQL Schema Migration Conflict | Medium | Low | EF Core migrations will be reviewed by Architect before every production deploy. Staging environment mirrors prod — all migrations tested in staging first. Point-in-time recovery available if rollback needed. |
| Twilio DLT Registration Delay (SMS India) | Low | Medium | India's TRAI DLT registration for transactional SMS can take 1–2 weeks. Mitigation: initiate registration in Week 1 alongside development. WhatsApp OTP used as fallback during DLT pending period. |
| Firebase Auth Outage | Medium | Very Low | Firebase has 99.99% monthly uptime SLA. Mitigation: JWT tokens have 1-hour validity so brief outages do not log out active users. Offline mode caches last valid session. |
| CloudFront Video Egress Cost Spike | Medium | Low | Set CloudFront data transfer budget alarm at ₹8,000/mo in CloudWatch. Implement server-side pagination and lazy loading to avoid bulk pre-fetches. S3 Lifecycle policies archive old videos to Glacier. |
| Scope Creep Post Gate 1 | High | Medium | Formal Change Request process mandated after Week 2 sign-off. All post-gate changes go to Phase 2 backlog. Written CR required with cost and timeline delta — no verbal approvals. |
| iOS App Store Review Delay | Medium | Low | Apple review averages 24–48 hours but can extend to 7 days. Mitigation: submit binary by end of Week 9 (not Week 10) to absorb delays. Expedite review available for critical bugs. |
| PostgreSQL Connection Pool Exhaustion at Scale | Medium | Very Low | At ANM's expected scale (500–1,000 MAU), RDS connection pool will not be saturated. PgBouncer connection pooler can be added in Phase 2 if user base grows beyond 5,000 MAU. |
| Team .NET 8 Skill Gap | Medium | Low | Team has experience with proprietary .NET 8 framework. Junior team members onboarded via pair programming in Week 1. .NET 8 documentation and training resources are comprehensive. |
| AWS Cost Overrun | Low | Low | CloudWatch billing alarms set at 80% and 100% of monthly budget. ECS auto-scaling max cap of 10 tasks prevents runaway compute. RDS instance right-sizing reviewed quarterly. |

# 6. Team & Capability Feasibility

## 6.1  Required Skills vs. Team Profile

| Role | Key Skills Required | Availability | Feasibility Note |
| --- | --- | --- | --- |
| Project Manager | Agile PM, client comms, risk | Full (Wks 1–10) | Assigned. Experienced in .NET delivery and stakeholder management. |
| Solution Architect | .NET 8, PostgreSQL, AWS architecture | Part-time (gates) | Assigned. Reviews schema, API contracts, and sign-off gates. |
| UI/UX Designer | Figma, Ionic, mobile UX patterns | Full (Wks 1–7) | Assigned. Ionic design system experience; Figma delivery in Week 2. |
| Mobile Developer (Sr.) | React, Ionic 7, Capacitor, TypeScript | Full (Wks 2–10) | Assigned. Experience with Ionic and Capacitor native bridge integrations. |
| Backend Developer (Sr.) | C#, .NET 8, EF Core, PostgreSQL | Full (Wks 1–10) | Assigned. Prior .NET 8 production experience with the framework. |
| DevOps Engineer | AWS ECS, RDS, GitHub Actions, Docker | Part-time + surge | Assigned. AWS Certified Solutions Architect. |
| QA Engineer | xUnit, Playwright, Appium 2.x | Ramps Wk 7 | Assigned. Playwright + Appium experience. Testcontainers onboarding in Week 1. |
| Security Consultant | OWASP Mobile Top 10, pentest, JWT | Wks 9–10 only | Assigned. OWASP-certified. Written pentest report delivered with results. |

# 7. Timeline Feasibility

## 7.1  Why 10 Weeks is Achievable

The 10-week delivery timeline is feasible — not because corners are cut, but because the proprietary enterprise framework eliminates 40–60% of boilerplate development that would otherwise be required in a greenfield build.

| Phase | Duration | Sprint | Key Deliverables |
| --- | --- | --- | --- |
| Phase 1: Discovery & Config | Wk 1–2 | Sprint 1 | Stakeholder workshops, DB schema, CI/CD, Ionic scaffold, Figma sign-off (Gate G1) |
| Phase 2: Core Customisation | Wk 3–6 | Sprints 2–3 | Auth, Member Directory, History, Prayer Requests, Video Library (Gate G2 at Wk 6) |
| Phase 3: Feature Completion | Wk 7–8 | Sprint 4 | Twilio Chat/VoIP, FCM Push, Admin RBAC, Group features, performance audit |
| Phase 4: QA, UAT & Launch | Wk 9–10 | Sprint 5 | xUnit + Playwright + Appium, OWASP, UAT, App Store submission (Gate G3 at Wk 10) |
| Hypercare (Free 30 days) | HC 1–2 | – | Bug fixes, monitoring, admin training, source code handover, Phase 2 planning |

## 7.2  Framework Acceleration Factor

The proprietary enterprise framework contributes pre-built modules that directly eliminate development work from the critical path:

| Module | Greenfield (days) | With Framework (days) | Time Saved |
| --- | --- | --- | --- |
| Firebase Auth + JWT Middleware | 5–8 days | 0.5 days | Module pre-built; configure ANM client ID only |
| Base .NET 8 API scaffold + DI setup | 4–6 days | 0 days | Framework includes full middleware, health checks, OpenAPI |
| EF Core 8 base + migration pipeline | 3–4 days | 0.5 days | Migrations pattern established; add ANM schema entities only |
| AWS S3 + CloudFront media pipeline | 6–8 days | 1 day | Pre-built upload/signed URL pattern; configure ANM bucket |
| SignalR WebSocket hub base | 3–5 days | 0.5 days | Hub pattern pre-built; add ANM-specific events |
| CI/CD GitHub Actions + ECS pipeline | 4–5 days | 0.5 days | Reusable workflow; configure ECS service name only |
| Role-based auth (RBAC) middleware | 3–4 days | 0 days | Already in framework as configurable policy |
| Ionic base project + dark mode | 2–3 days | 0.5 days | Scaffold with bottom nav, routing, theme vars ready |

# 8. Infrastructure & Financial Feasibility

## 8.1  Implementation Cost Summary (INR)

Implementation: One-time fixed-price engagement ¦ All amounts in INR Starter Package: ₹32,00,000 (10 weeks, core features — Auth, Directory, Prayer, Video) Standard Package: ₹38,00,000 (10 weeks, + Twilio Chat/VoIP, FCM, CloudFront, CI/CD, 30-day HC) Enterprise Package: ₹48,00,000 (10 weeks, + Group Chat, Admin Dashboard, Multi-language, 12-mo SLA)

## 8.2  Ongoing Monthly Costs (Client-Borne)

| Service | Monthly Cost (₹) | Notes |
| --- | --- | --- |
| AWS RDS PostgreSQL 16 (db.t4g.medium, Multi-AZ) | ₹18,500 | Managed DB with automated backups + failover |
| AWS ECS Fargate (2 tasks, 1 vCPU / 2 GB each) | ₹12,000 | Scales 1–10 tasks on demand |
| AWS S3 + CloudFront CDN (250 GB + 1 TB egress) | ₹6,000 | Video library storage + global CDN |
| AWS CloudWatch + Application Load Balancer | ₹3,500 | Monitoring, alerting, WAF rate limiting |
| Twilio Voice + SMS + Conversations Chat | ₹4,825 | Usage-based; scales with call/message volume |
| Firebase Auth + FCM | Free | Up to 10,000 auth verifications/month free |
| TOTAL MONTHLY INFRASTRUCTURE | ₹44,825 | Approx. at 500–1,000 MAU user base |

## 8.3  AMC Options (Post-Warranty)

Following the 30-day free Hypercare period, ANM should engage an Annual Maintenance Contract to ensure continued bug fixes, security patching, and SLA-backed support.

| Tier | Monthly (₹) | Annual (₹) | Key Inclusions |
| --- | --- | --- | --- |
| Basic | ₹15,000 | ₹1,80,000 | Bug fixes, OS compatibility, monthly health check, 48h SLA |
| Standard | ₹25,000 | ₹3,00,000 | Basic + 2 minor enhancements/quarter, 8-hour SLA, priority queue |
| Premium | ₹40,000 | ₹4,80,000 | Standard + 20 dev hours/month, 2-hour SLA, dedicated support manager |

# 9. Conclusion & Recommendation

OVERALL FEASIBILITY: APPROVED The proposed technology stack is technically sound, commercially viable, team-ready, and timeline-achievable. We recommend proceeding with the Standard Package at ₹38L for the 10-week delivery.

## 9.1  Summary Scorecard

| Feasibility Dimension | Score | Summary |
| --- | --- | --- |
| Technical Stack Viability | ★★★★★ | All technologies production-proven; no experimental dependencies |
| Team Capability | ★★★★☆ | All roles assigned; minor Appium onboarding in Week 1 |
| Timeline (10 Weeks) | ★★★★☆ | Feasible with framework acceleration; buffer in Sprint 5 |
| Infrastructure Readiness | ★★★★★ | AWS ECS Fargate + RDS ready to provision; no blockers |
| Financial Viability | ★★★★★ | Clear pricing; monthly costs transparent and controllable |
| Risk Profile | ★★★★☆ | No showstopper risks; 3 medium risks with clear mitigations |
| Scalability (Phase 2+) | ★★★★★ | Stack scales to 50,000+ MAU without architecture change |
| Security & Compliance | ★★★★★ | OWASP, JWT, WAF, RDS encryption, SSM secrets — fully covered |

## 9.2  Next Steps

Upon acceptance of this feasibility study, the following actions initiate the delivery:

- Sign the engagement agreement and release the 30% kickoff deposit

- Week 1, Day 1: Kickoff meeting with ANM leadership and development team

- Week 1: Initiate Twilio DLT registration for SMS (India TRAI compliance)

- Week 1: Firebase project creation, AWS account access, GitHub repo provisioning

- Week 2: Figma high-fidelity designs delivered for Gate G1 sign-off

- Week 2: PostgreSQL schema and API contract (OpenAPI spec) approved

- Ongoing: Weekly demo calls every Friday with ANM stakeholders

RECOMMENDATION: Proceed with Standard Package — ₹38,00,000 Delivery: 10 weeks to App Store + Play Store live Post-launch: Standard AMC at ₹25,000/month for SLA-backed support Monthly infrastructure: ~₹44,825 (AWS + Twilio) — client-borne, transparent

Prepared by: Solution Development Team   |   Date: June 2025   |   Version: v1.0 — Draft for Review

This document is confidential and prepared exclusively for ANM. Do not distribute without written permission from Solution Development Team.