## Slide 1
PROJECT PLANNING DOCUMENT · v1.0
Delivery Milestone &
Implementation Plan
ANM Community Mobile App — End-to-End Execution Roadmap
Sprints · Milestones · RACI · Dependencies · Go-Live Checklists
PROJECT
ANM Community App
DURATION
8–10 Weeks (MVP)
METHODOLOGY
Agile / 2-Week Sprints
VERSION
v1.0 — Draft
Confidential | ANM Community App

## Slide 2
OVERVIEW
Plan at a Glance
5
Delivery Phases
Discovery → Support
18
Key Milestones
4 Formal Sign-off Gates
5
Agile Sprints
2 Weeks Each
132
Story Points
Across All Sprints
9
Weeks to Go-Live
App Store + Play Store
40+
Checklist Items
Pre-launch Verification
ANM Community App · Delivery Milestone & Implementation Plan · v1.0 · Confidential

## Slide 3
PART ONE — DELIVERY MILESTONE PLAN
Project Gantt — 10-Week Overview
Wk 1
Wk 2
Wk 3
Wk 4
Wk 5
Wk 6
Wk 7
Wk 8
Wk 9
Wk 10
DELIVERABLE
📐 PHASE 1 — DISCOVERY
Stakeholder Workshops
Wireframes & Design
DB Schema & API Contract
CI/CD & Env Setup
⚙️ PHASE 2 — DEVELOPMENT
Auth + Onboarding
Member Directory+Detail
Prayer Requests+History
Video Library+Streaming
Messaging & VoIP
🧪 PHASE 3 — QA
Unit+Integration Tests
E2E & Perf Testing
UAT with ANM Team
🚀 PHASE 4 — DEPLOY
Store Submissions
Backend Prod Deploy
🔄 PHASE 5 — SUPPORT
Hypercare+Monitoring
ANM Community App · Delivery Milestone & Implementation Plan · v1.0 · Confidential

## Slide 4
PART ONE — DELIVERY MILESTONE PLAN
Milestone Register (1 of 2) — M1 to M9
#
Milestone
Week
Owner
Type
Success Criteria
1
Project Kickoff
Wk 1 Day 1
PM
Gate
All stakeholders aligned on scope, timeline & comms cadence
2
Requirements Sign-Off
Wk 1 Day 3
PM + ANM PO
Sign-off
ANM PO formally approves feature list & out-of-scope items
3
Wireframes Delivered
Wk 1 End
UI/UX Designer
Planned
All 5 screens covered; navigation flow approved by ANM team
4
Design System Approved
Wk 2 Mid
UI/UX Designer
Planned
Typography, colours, spacing & components locked for dev handoff
5
Architecture Sign-Off
Wk 2 End
Architect + PM
Sign-off
DB schema, API contract & infra reviewed & approved
6
Dev Environments Live
Wk 2 End
DevOps
Planned
CI/CD pipeline runs; all 3 environments accessible; Atlas provisioned
7
Auth + Onboarding Live
Wk 3 End
Mobile Dev
Planned
Users can register, verify OTP & log in on iOS & Android
8
Mid-Sprint Demo #1
Wk 4 End
PM + Dev Team
Demo
ANM team sees Members Directory, Detail & History on device
9
Prayer Requests Complete
Wk 5 Mid
Backend + Mobile
Planned
Submit (incl. anonymous), browse, and respond to prayer requests
ANM Community App · Delivery Milestone & Implementation Plan · v1.0 · Confidential

## Slide 5
PART ONE — DELIVERY MILESTONE PLAN
Milestone Register (2 of 2) — M10 to M18
#
Milestone
Week
Owner
Type
Success Criteria
10
Video Library Complete
Wk 5 End
Backend + DevOps
Planned
Videos stream from S3/CDN; category filtering works on device
11
Mid-Sprint Demo #2
Wk 6 Mid
PM + Dev Team
Demo
ANM team sees working in-app chat and VoIP calling
12
MVP Feature-Complete
Wk 6 End
Solution Architect
Sign-off
100% Phase 1 stories Done; no P1 bugs open; code review passed
13
Test Coverage Target Met
Wk 7 End
QA Engineer
Planned
≥80% unit coverage; all 17 API endpoints covered; E2E pass
14
Security Audit Clear
Wk 8 Mid
Security Consultant
Planned
No critical/high OWASP Mobile Top 10 vulnerabilities found
15
UAT Sign-Off
Wk 8 End
ANM PO
Sign-off
ANM approves all features on TestFlight & internal Play track
16
Store Submissions Filed
Wk 9 Day 1
Mobile Dev + PM
Planned
Both submissions in review (Apple 24–48hr, Google 24–72hr)
17
🚀 Production Go-Live
Wk 9 End
Full Team
Go-Live
App live on App Store & Google Play; backend healthy; monitoring active
18
Hypercare Handover
Wk 10
PM + DevOps
Planned
Admins trained; runbooks delivered; CloudWatch live; SLA active
ANM Community App · Delivery Milestone & Implementation Plan · v1.0 · Confidential

## Slide 6
PART TWO — IMPLEMENTATION PLAN
Phase-by-Phase Breakdown
Phase 01
Discovery & Design
Wks 1–2
› Stakeholder workshops (×2)
› User journey mapping
› Feature list finalisation
› Lo-fi → Hi-fi wireframes
› Design system & components
› MongoDB schema design
› REST API contract doc
› Dev / staging / prod setup
› CI/CD pipeline (GH Actions)
› RN project scaffold + lint
Phase 02
Core Development
Wks 3–6
› Firebase Auth (OTP + biometric)
› Onboarding (3-step flow)
› Member directory API + UI
› Member detail & edit
› Member history notes log
› Prayer request CRUD + anon
› Prayer feed + Pray response
› S3 upload + presigned URLs
› CloudFront streaming + UI
› Twilio Chat 1:1 messaging
› Twilio Voice VoIP calling
› Deep linking + nav polish
Phase 03
Testing & QA
Wks 7–8
› Jest unit tests (≥80% cov.)
› Supertest API integration
› Detox E2E — iOS Simulator
› Detox E2E — Android Emulator
› k6 load test (500 users)
› Video streaming latency test
› VoiceOver + TalkBack audit
› WCAG 2.1 AA contrast checks
› OWASP penetration test
› UAT — 20 ANM pilot members
› P1/P2 bug fix sprint
› Regression after bug fixes
Phase 04
Deployment
Week 9
› Prod MongoDB Atlas config
› ECS Fargate task definitions
› CloudFront CDN finalise
› DNS records + SSL (ACM)
› CloudWatch alarms + dashboards
› Sentry crash monitoring setup
› App Store submission (EAS)
› Google Play submission (AAB)
› Phased rollout 10% → 100%
› Go-live smoke test on prod
Phase 05
Support & Phase 2
Wk 10+
› 30-day hypercare on-call
› ANM admin training (2 hrs)
› Runbook & docs delivery
› OS update testing
› Monthly infra cost review
› Phase 2 backlog grooming
› Push notifications (FCM)
› Group chat / forums
› Multi-language i18n setup
› Admin dashboard scoping
ANM Community App · Delivery Milestone & Implementation Plan · v1.0 · Confidential

## Slide 7
PART TWO — SPRINT BREAKDOWN
Sprint 1 & 2 — Foundation + Auth & Members
Sprint 1 — Discovery & Setup
Weeks 1–2
3
Stakeholder workshop & requirements doc
PM | 2 sessions, signed off by ANM PO
5
Hi-fi wireframes — all 5 screens
UI/UX Designer | Figma, all states covered
3
Design system & component library
UI/UX Designer | Colours, type, atoms
5
DB schema + API contract doc
Backend + Architect | 5 collections, 17 endpoints
5
CI/CD pipeline + environments
DevOps | GitHub Actions, EAS, 3 environments
2
React Native project scaffold
Mobile Dev | ESLint, Prettier, nav structure
Total Story Points
23 pts
Sprint 2 — Auth & Members
Weeks 3–4
5
Firebase Auth — email/phone OTP
Mobile Dev | Sign up, OTP verify, login
3
Biometric login (Face ID / Fingerprint)
Mobile Dev | iOS & Android local auth
3
Onboarding flow — 3-step profile setup
Mobile Dev | Photo upload, name, group
5
Member directory API + UI
Backend + Mobile | Search, filter, pagination
5
Member detail & profile edit screens
Mobile Dev | Contact info, role badge, actions
4
Member history — notes log
Backend + Mobile | Leader-only add/view
2
Home dashboard screen
Mobile Dev | Tiles, greeting, nav
Total Story Points
27 pts
ANM Community App · Delivery Milestone & Implementation Plan · v1.0 · Confidential

## Slide 8
PART TWO — SPRINT BREAKDOWN
Sprint 3 & 4 — Prayer & Media + QA & Hardening
Sprint 3 — Prayer & Media
Weeks 5–6
5
Prayer request submission + anon mode
Backend + Mobile | Form, CRUD, status
4
Prayer request feed + Pray response
Mobile Dev | Scrollable feed, tap-to-pray
4
AWS S3 upload pipeline + presigned URLs
Backend + DevOps | Admin video upload
4
CloudFront streaming + video library UI
Mobile Dev | Categories, thumbnails, player
6
Twilio Chat SDK — 1:1 messaging
Mobile Dev | Real-time, read receipts, history
6
Twilio Voice SDK — VoIP calling
Mobile Dev | In-app call, no phone # shared
2
Deep linking + bottom nav polish
Mobile Dev | Universal links, tab state
Total Story Points
31 pts
Sprint 4 — QA & Hardening
Weeks 7–8
5
Jest unit tests — ≥80% coverage
QA + Backend | All service-layer logic
4
Supertest API integration tests
QA | All 17 endpoints, +/- paths
6
Detox E2E — iOS + Android
QA | Login, member, pray, video, call
3
k6 performance + load testing
DevOps + QA | 500 concurrent users
3
Accessibility audit — VoiceOver/TalkBack
QA + Designer | WCAG 2.1 AA
4
OWASP penetration test + security fixes
Security Consultant | Top 10 review
4
UAT with 20 ANM pilot members
PM + QA | TestFlight + Play internal
3
P1/P2 bug fix sprint + regression
Dev Team | All critical issues resolved
Total Story Points
32 pts
ANM Community App · Delivery Milestone & Implementation Plan · v1.0 · Confidential

## Slide 9
PART TWO — SPRINT BREAKDOWN
Sprint 5 — Deploy & Launch + Effort Summary
Sprint 5 — Deploy & Launch
Weeks 9–10
3
Production infrastructure provisioning
DevOps | ECS, MongoDB Atlas M10, CloudFront
2
CloudWatch alarms + dashboards
DevOps | API latency, error rate, uptime
2
Sentry crash monitoring setup
DevOps + Mobile | iOS + Android DSN
3
Apple App Store submission
Mobile Dev | EAS Build, review guidelines
3
Google Play Console submission
Mobile Dev | Internal → prod release (AAB)
2
Go-live smoke test on production
QA + PM | All critical paths verified
2
ANM admin training session
PM | 2-hr session: uploads, member mgmt
2
Runbooks + admin docs delivery
DevOps + PM | Incident response, escalation
Total Story Points
19 pts
📊 Effort Summary
Sprint 1
Discovery & Setup
23
pts
Sprint 2
Auth & Members
27
pts
Sprint 3
Prayer & Media
31
pts
Sprint 4
QA & Hardening
32
pts
Sprint 5
Deploy & Launch
19
pts
TOTAL
132 story points
ANM Community App · Delivery Milestone & Implementation Plan · v1.0 · Confidential

## Slide 10
PART TWO — ROLES & RESPONSIBILITIES
RACI Matrix
R
Responsible — Does the work
A
Accountable — Owns the outcome
C
Consulted — Input required
I
Informed — Kept in the loop
Activity
PM
Designer
Mobile Dev
Backend
DevOps
QA
Security
Architect
ANM PO
Requirements Gathering
A
C
C
C
I
I
I
C
R
Wireframes & Design
I
R/A
C
I
I
C
I
C
C
Architecture Design
I
I
C
R
R
I
C
A
I
DB Schema & API Design
I
I
C
R
I
I
I
A
I
CI/CD & Infra Setup
I
I
C
C
R/A
I
C
C
I
Mobile App Development
I
C
R/A
C
I
C
I
C
I
Backend API Development
I
I
C
R/A
C
C
I
C
I
Unit & Integration Testing
I
I
R
R
I
A
I
C
I
E2E & Performance Testing
I
I
C
C
C
R/A
I
I
I
Security Audit
I
I
C
C
C
C
R/A
C
I
UAT Coordination
R
I
C
C
I
R
I
I
A
App Store Submissions
A
I
R
I
C
C
I
I
I
Production Deployment
A
I
C
C
R
C
I
C
I
Stakeholder Reporting
R/A
I
I
I
I
I
I
I
C
Change Request Management
R
C
C
C
C
C
I
A
R
ANM Community App · Delivery Milestone & Implementation Plan · v1.0 · Confidential

## Slide 11
PART TWO — IMPLEMENTATION PLAN
Key Dependencies & Blockers
#
Dependency
Due
Owner
Risk
Contingency
D1
ANM signs contract & SOW
Before Wk 1
PM + ANM PO
High
No work begins until signed. PM to chase 5 days before planned start.
D2
ANM brand assets (logo, colour guide)
Wk 1 Day 2
ANM PO
Med
Proceed with placeholder brand; swap assets when received.
D3
Firebase project credentials provisioned
Wk 2 End
DevOps
High
Create shared Firebase project in advance; transfer ownership post-launch.
D4
Twilio account & API keys
Wk 4 End
DevOps
Med
Use Twilio trial for dev; upgrade to production before Wk 9.
D5
AWS account with required service limits
Wk 1 End
DevOps
High
Request limit increases on Day 1 — AWS takes 24–48 hrs.
D6
Apple Developer Account (ANM enrolled)
Wk 4
ANM PO
Med
Enrolment takes up to 7 business days — must begin Wk 3.
D7
Google Play Developer Account (ANM)
Wk 4
ANM PO
Med
One-time $25 fee; approval usually same day.
D8
UAT pilot members identified & invited
Wk 6
ANM PO
Low
QA team can use internal testers if ANM pilot unavailable.
D9
ANM video content for library seed
Wk 4
ANM PO
Low
Use 3 placeholder videos during dev; replace before go-live.
ANM Community App · Delivery Milestone & Implementation Plan · v1.0 · Confidential

## Slide 12
PART TWO — GO-LIVE CHECKLISTS
Infrastructure & Monitoring Checklists
☁️ Infrastructure & Cloud
AWS RDS PostgreSQL 16 (db.r6g.large) Multi-AZ provisioned in prod region
RDS security group: port 5432 inbound from ECS task CIDR only
AWS ECS Fargate production service created
Auto-scaling policy: CPU ≥ 70% → scale out
S3 production bucket — versioning enabled
CloudFront distribution live with custom domain
ACM SSL certificate issued & attached to ALB
DNS records pointing to ALB (api.anm.org)
Secrets Manager storing all env variables
VPC with private subnets for ECS tasks
📊 Monitoring & Observability
CloudWatch dashboard — API latency, error rate, 5xx count
CloudWatch alarm: API error rate > 1% → alert
CloudWatch alarm: ECS CPU > 80% for 5 min
CloudWatch alarm: RDS PostgreSQL connections > 80% pool
Sentry project created for iOS app (DSN configured)
Sentry project created for Android app (DSN configured)
Log retention policy set (30d dev, 90d prod)
Health check endpoint /health returning 200
On-call rotation schedule documented
ANM Community App · Delivery Milestone & Implementation Plan · v1.0 · Confidential

## Slide 13
PART TWO — GO-LIVE CHECKLISTS
Security & App Store Go-Live Checklists
🔒 Security & Auth
Firebase PRODUCTION project created (separate from dev)
JWT expiry: 1 hr with refresh token rotation
All API endpoints require valid JWT (except /auth/*)
Rate limiting: 100 req/min per IP on API Gateway
CORS whitelist: only ANM app bundle IDs allowed
RDS PostgreSQL encryption at rest confirmed (AWS KMS default)
TLS 1.3 enforced on all HTTPS endpoints
S3 public access blocked — only CloudFront reads
OWASP findings resolved — report signed off
Privacy policy linked in app onboarding screen
📱 App Store & Go-Live
App Store listing: screenshots, description, keywords
App Store privacy manifest submitted (iOS 17+)
App icons: all required sizes (iOS + Android)
Splash screens: iOS + Android all densities
Google Play: feature graphic, screenshots, rating questionnaire
EAS production build tested on physical devices
Deep links tested: iOS Universal Links + Android App Links
Production API base URL in release build
Go-live smoke test completed (all 5 critical paths)
Phased rollout set to 10% on both stores
ANM team notified; member comms ready to send
ANM Community App · Delivery Milestone & Implementation Plan · v1.0 · Confidential

## Slide 14
PART TWO — COMMUNICATION PLAN
Communication & Reporting Cadence
Meeting / Report
Frequency
Participants
Format
Owner
Sprint Planning
Every 2 wks (Mon Wk 1)
Full dev team
2-hr Zoom
PM
Daily Stand-up
Daily Mon–Fri (15 min)
Dev team
Async Slack / 9am call
PM
Weekly ANM Update
Every Friday
PM + ANM PO
Email summary
PM
Sprint Demo
End of every sprint (Fri)
Full team + ANM stakeholders
60-min live demo on device
PM + Lead Dev
Sprint Retrospective
Every 2 weeks post-demo
Dev team only
30-min debrief
PM
Design Review
Wk 1 & 2 (ad hoc)
Designer + ANM PO + PM
Figma walkthrough
Designer
Architecture Review
Wk 2 (once)
Architect + Backend + DevOps
Diagram review
Architect
UAT Feedback Session
Wk 8 (2 sessions)
ANM pilot + QA + PM
Zoom with screen share
PM + QA
Go-Live Readiness Review
Wk 9 Day 1
Full team + ANM PO
Checklist review (45 min)
PM + Architect
Monthly Infra Report
Monthly (post-launch)
PM + ANM PO
Email: cost, uptime, usage
DevOps + PM
⚠ Change Control: Scope changes require a formal CR after Milestone 5 (Architecture Sign-Off). Architect assesses impact within 48 hrs; PM updates milestone plan accordingly.
ANM Community App · Delivery Milestone & Implementation Plan · v1.0 · Confidential

## Slide 15
✅
Ready to Execute
This plan gives ANM full visibility into every milestone, sprint, dependency,
and go-live requirement — from Day 1 through to production launch and beyond.
18
Milestones Tracked
132
Story Points Planned
40+
Go-Live Checklist Items
9 Wks
To App Store Launch
📅
Schedule Kickoff
Book discovery call with ANM leadership
📄
Sign & Start
30% deposit kicks off Week 1 immediately
❓
Questions?
hello@yourstudio.com
ANM Community App · Delivery Milestone & Implementation Plan · June 2025 · Private & Confidential