## Assumptions
ANM Community App — Resource & Pricing Assumptions
Project | ANM Community App
Client | ANM — Church & Community Platform
Prepared by | Solution Development Team
Date | June 2025
Currency | USD ($)
Version | v1.0 — Draft
RATE CARD — Daily Rates (USD)
Role | Daily Rate (USD) | Role ID | Notes / Scope
Project Manager | 900 | PM | Sr PM; reporting, risk, ANM stakeholder comms
Solution Architect | 1200 | ARC | Architecture reviews & formal sign-off gates
UI/UX Designer | 800 | DES | Figma, design system, UAT design support
Mobile Developer (Sr.) | 950 | MOB | React Native — iOS & Android cross-platform
Backend Developer (Sr.) | 950 | BAK | Node.js / Express, MongoDB Atlas, REST APIs
DevOps Engineer | 850 | DEV | AWS ECS, CI/CD, S3/CloudFront, monitoring
QA Engineer | 750 | QA | E2E, unit, load, accessibility testing
Security Consultant | 1100 | SEC | OWASP pentest, audit & sign-off report
PRICING ASSUMPTIONS
Parameter | Value |  | Notes
Gross Margin % (on cost) | 50% |  | 50% margin added on top of total cost → client price
Working Days / Week | 5 |  | Mon–Fri; excludes public holidays & bank holidays
Hypercare Duration (weeks) | 2 |  | Post go-live monitoring & support period
Sprint Length (weeks) | 2 |  | Agile: 2-week sprint cadence (5 sprints total)
Project Duration — Core (wks) | 10 |  | Wk 1 through Wk 10 (Discovery → Go-Live)
Total Duration incl. HC (wks) | 12 |  | Core 10 weeks + 2 hypercare weeks
COLOR CODING LEGEND
Blue text | (sample) |  | Hardcoded input — users may change these for scenario analysis
Black text | (sample) |  | Excel formula / calculated value — do not edit manually
Green text | (sample) |  | Link pulling from another worksheet within this workbook

## Resource Plan
ANM Community App — Resource Loading Plan (Team-Days per Week)
PHASE | Phase 1: Discovery & Design |  | Phase 2: Core Development |  |  |  | Phase 3: QA & Testing |  | Phase 4: Deployment | Phase 5: Hypercare |  |  | TOTAL | FTE | Phase Focus
Role | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | HC-1 | HC-2 | Days | ÷50d | Notes
Project Manager | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 4 | 2 | 2 |  |  | Discovery → Go-Live → Hypercare oversight
Solution Architect | 5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | Discovery, architecture gate & QA gate only
UI/UX Designer | Phase 1: Discovery & Design Wk 1: 5; Phase 1: Discovery & Design Wk 2: 5; Phase 2: Core Development Wk 3: 2; Phase 2: Core Development Wk 4: 2; Phase 2: Core Development Wk 5: 1; Phase 2: Core Development Wk 6: 1 |  |  | Design-heavy in Wks 1–4; wraps up Wk 6
Mobile Developer (Sr.) |  | 1 | 5 | 5 | 5 | 5 | 3 | 3 | 4 | 2 | 2 | 2 |  |  | Full dev sprints 2–5; bug-fix in QA & HC
Backend Developer (Sr.) | 2 | 2 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 1 | 2 | 2 |  |  | API design Wks 1–2; full from Wk 3 onward
DevOps Engineer | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 4 | 3 | 3 |  |  | Env setup Wks 1–2; full prod deploy Wk 9
QA Engineer |  |  | 1 | 1 | 1 | 1 | 5 | 5 | 3 | 1 | 1 | 1 |  |  | Light in dev; full engagement Wks 7–8
Security Consultant | Phase 3: QA & Testing Wk 7: 4; Phase 3: QA & Testing Wk 8: 4 |  |  | OWASP pentest Wks 7–8 only; written report
TOTAL TEAM-DAYS / WEEK
Max capacity (8 roles × 5d) | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Utilisation %
PHASE SUMMARY
Phase | Phase 1: Discovery & Design Wk 1: Weeks; Phase 1: Discovery & Design Wk 2: Team-Days; Phase 2: Core Development Wk 3: % of Total; Phase 2: Core Development Wk 4: Avg daily headcount
Phase 1: Discovery & Design | Phase 1: Discovery & Design Wk 1: Wks 1–2
Phase 2: Core Development | Phase 1: Discovery & Design Wk 1: Wks 3–6
Phase 3: QA & Testing | Phase 1: Discovery & Design Wk 1: Wks 7–8
Phase 4: Deployment | Phase 1: Discovery & Design Wk 1: Wk 9
Phase 5: Hypercare (Wk10+HC) | Phase 1: Discovery & Design Wk 1: Wks 10–12
TOTAL | Phase 1: Discovery & Design Wk 1: 12 wks

## Cost Model
ANM Community App — Cost Build-up & Pricing Model
Green = cross-sheet link · Blue = editable input · Black = formula · Margin applied in rows 14–17 · Amounts in USD
Role | Daily Rate (USD) | Project Days (Wks 1–10) | HC Days (2 wks) | Total Days | Project Cost (USD) | HC Cost (USD) | Total Cost (USD) | % of Total | Source / Notes
Project Manager | [8 empty] | Source: Assumptions!B13 ¦ Days: Resource Plan rows 4, cols B:K and L:M
Solution Architect | [8 empty] | Source: Assumptions!B14 ¦ Primarily Wks 1–2; gates in later phases
UI/UX Designer | [8 empty] | Source: Assumptions!B15 ¦ Design-heavy Wks 1–4; wraps by Wk 6
Mobile Developer (Sr.) | [8 empty] | Source: Assumptions!B16 ¦ Full sprints Wks 3–8; part-time in HC
Backend Developer (Sr.) | [8 empty] | Source: Assumptions!B17 ¦ Full sprints Wks 3–8; part-time in HC
DevOps Engineer | [8 empty] | Source: Assumptions!B18 ¦ Env setup Wks 1–2; full deployment Wk 9
QA Engineer | [8 empty] | Source: Assumptions!B19 ¦ Full engagement Wks 7–8 QA phase
Security Consultant | [8 empty] | Source: Assumptions!B20 ¦ OWASP pentest Wks 7–8 only; fixed scope
TOTAL COST (before margin) | [7 empty] | 100.0%
Total Cost (USD)
Gross Margin % (50%)
Margin Amount (USD)
TOTAL CLIENT PRICE (USD)
COST & PRICE BY DELIVERY PHASE
Phase | Weeks | Team-Days | Proportional Cost (USD) | Selling Price incl. 50% Margin | % of Total Price
Phase 1: Discovery & Design | Wks 1–2
Phase 2: Core Development | Wks 3–6
Phase 3: QA & Testing | Wks 7–8
Phase 4: Deployment | Wk 9
Phase 5: Hypercare (Wk10+HC) | Wks 10–12
TOTAL | 12 wks

## Weekly Cost
ANM Community App — Weekly Cost Breakdown & Cash Flow
Costs = days (Resource Plan) × rate (Assumptions) · Selling price = cost × (1 + 50% margin) · Amounts in USD
Week | Phase | PM | Architect | Designer | Mobile Dev | Backend Dev | DevOps | QA | Security | Total Cost /Wk (USD) | Cumul. Cost (USD) | Sell Price /Wk (USD) | Cumul. Sell Price (USD)
Wk 1 | Phase 1: Discovery & Design
Wk 2 | Phase 1: Discovery & Design
Wk 3 | Phase 2: Core Development
Wk 4 | Phase 2: Core Development
Wk 5 | Phase 2: Core Development
Wk 6 | Phase 2: Core Development
Wk 7 | Phase 3: QA & Testing
Wk 8 | Phase 3: QA & Testing
Wk 9 | Phase 4: Deployment
Wk 10 | Phase 5: Hypercare
HC-Wk1 | Phase 5: Hypercare
HC-Wk2 | Phase 5: Hypercare
TOTAL
COST SUMMARY BY PHASE
Phase | Weeks | Team-Days | Cost (USD) | Selling Price (USD) | % of Total
Phase 1: Discovery & Design | Wks 1–2
Phase 2: Core Development | Wks 3–6
Phase 3: QA & Testing | Wks 7–8
Phase 4: Deployment | Wk 9
Phase 5: Hypercare (Wk10+HC) | Wks 10–12
TOTAL | 12 wks