## Assumptions
MAHIMA ANM PLATFORM — PROJECT ASSUMPTIONS
All rates are USD per day (8-hour working day)
Colour key: 🔵 Blue = hardcoded input ¦ ⚫ Black = formula ¦ 🟢 Green = cross-sheet reference
RESOURCE RATE CARD
Role | Day Rate (USD) | Type | Notes
Project Manager | 900 | Management | Full 8-week engagement
Solution Architect | 1200 | Technical | Front-loaded Week 1–2
UI/UX Designer | 800 | Design | Phase 1–2 only
Full-Stack Dev (.NET 8) | 950 | Development | ASP.NET Core, C#, EF Core
Mobile Developer | 950 | Development | React+Capacitor, iOS build
DevOps Engineer | 850 | Infrastructure | AWS, CI/CD, Nginx
QA Engineer | 750 | Quality | Test automation + UAT
PROJECT SETTINGS
Parameter | Value | Unit | Notes
Implementation Weeks | 8 | Weeks | Core delivery weeks
Hypercare Weeks | 2 | Weeks | Free post go-live support
Total Project Duration |  | Weeks | Implementation + Hypercare
Working Days per Week | 5 | Days | Mon–Fri
Profit Margin Target | 50% | % | 50% markup on cost
Client Price (formula) |  | USD | Auto-calculated

## Resource Plan
RESOURCE LOADING MATRIX — 8-WEEK IMPLEMENTATION + 2-WEEK HYPERCARE
Blue=input ¦ Black=formula ¦ HC=Hypercare |  | ◀ IMPLEMENTATION PHASES ▶ | [7 empty] | HYPERCARE |  | TOTALS
Role | Day Rate | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | HC1 | HC2 | Total Days | Cost (USD) | Note
Project Manager | 900 | 5 | 5 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 |  |  | Full-project engagement
Solution Architect | 1200 | 4 | 3 | 1 |  |  |  |  | 1 |  |  |  |  | Front-loaded Weeks 1–2
UI/UX Designer | 800 | 4 | 5 | 3 | 1 | [8 empty] | Phases 1–2 only
Full-Stack Dev (.NET 8) | 950 | 1 | 2 | 5 | 5 | 5 | 3 | 1 |  | 1 |  |  |  | Core customisation
Mobile Developer | 950 |  | 1 | 2 | 3 | 4 | 5 | 3 | 1 | 1 | 1 |  |  | iOS + Android Capacitor
DevOps Engineer | 850 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 1 |  |  | AWS + CI/CD
QA Engineer | 750 |  |  | 1 | 1 | 1 | 1 | 4 | 3 | 1 | 1 |  |  | QA + UAT + security
TOTAL

## Cost Model
MAHIMA ANM PLATFORM — COST MODEL & PRICING
Line Item | Amount (USD) | Notes
A. RESOURCE COSTS (from Resource Plan)
Project Manager |  | Linked from Resource Plan sheet
Solution Architect |  | Linked from Resource Plan sheet
UI/UX Designer |  | Linked from Resource Plan sheet
Full-Stack Dev (.NET 8) |  | Linked from Resource Plan sheet
Mobile Developer |  | Linked from Resource Plan sheet
DevOps Engineer |  | Linked from Resource Plan sheet
QA Engineer |  | Linked from Resource Plan sheet
RESOURCE SUB-TOTAL |  | Sum of all role costs
B. PRICING BUILD-UP
TOTAL COST (BASE) |  | From resource sub-total
PROFIT MARGIN (50%) |  | Linked from Assumptions!B21
CLIENT PRICE (ONE-TIME) |  | Implementation customisation fee
FREE 1-MONTH HYPERCARE | 0 | ~$5,000 value included at no extra cost
C. YEAR 1 TOTAL COST OF OWNERSHIP
One-Time Customisation |  | Client price as above
AWS Infrastructure (12 months) | 1332 | ~$111/month × 12
Third-Party Services (12 months) | 180 | ~$15/month × 12
AMC Pro Care (10 months from M2) |  | $1,500/month × 10 months
YEAR 1 TOTAL (Pro AMC) |  | Full first-year investment

## Platform Charges
MAHIMA ANM PLATFORM — MONTHLY INFRASTRUCTURE & 3RD-PARTY CHARGES
Based on up to 500 ANM users · All prices USD/month estimates
Service | Cost/Month | Annual Cost | Notes
☁️ AWS INFRASTRUCTURE
EC2 t3.medium (App Server) | 35 |  | General-purpose compute, 2vCPU 4GB RAM
RDS db.t3.micro (PostgreSQL) | 25 |  | Managed PostgreSQL, 1vCPU 1GB RAM
S3 Storage 100GB + requests | 10 |  | File storage for attachments + backups
CloudFront CDN | 8 |  | Content delivery + HTTPS termination
Elastic Load Balancer (ALB) | 18 |  | High-availability traffic distribution
NAT Gateway (2 AZ) | 15 |  | Outbound internet for private subnets
Route 53 DNS | 1 |  | Domain routing + health checks
AWS TOTAL |  |  | Monthly AWS infrastructure estimate
🔌 THIRD-PARTY SERVICES
Twilio SMS (avg 1,000 SMS/mo) | 8 |  | ~$0.0079 per SMS to India
Twilio Phone Number | 1 |  | Monthly number rental
Firebase Auth (up to 50K MAU) | Free | $0 | Free tier — no cost
Email (MailKit + SMTP relay) | 5 |  | SendGrid free tier or Mailgun
Domain Name (annual ÷ 12) | 1 |  | Approx ₹800–1200/year
SSL Certificate (Let's Encrypt) | Free | $0 | Free — auto-renewed via Certbot
3RD-PARTY TOTAL |  |  | Monthly third-party estimate
TOTAL MONTHLY PLATFORM COST |  |  | Annual total platform charges

## AMC Plans
ANNUAL MAINTENANCE & SUPPORT (AMC) PLANS — POST GO-LIVE
Month 1 is FREE Hypercare (included in one-time cost). AMC billing begins Month 2.
Feature / Parameter | Starter Care | Pro Care ★ | Enterprise Care | Starter Annual | Pro Annual | Enterprise Annual
Monthly Price (USD) | $800 | $1,500 | $2,500
Annual Price (USD) | $8,000 | $15,000 | $25,000
Annual Saving vs Monthly | $1,600 | $3,000 | $5,000
Bug Fixes & Security Patches | ✓ | ✓ | ✓
OS & Dependency Updates | ✓ | ✓ | ✓
Monthly Health Report | ✓ | ✓ | ✓
Support Hours / Month | 3 hrs | 6 hrs | 15 hrs
Response SLA | 48 hrs | 24 hrs | 4 hrs
CloudWatch Monitoring Review | — | ✓ | ✓
DB Performance Tuning | — | ✓ | ✓
Minor Feature Enhancements | — | ✓ | ✓
New Feature Development | — | — | ✓ (15hrs)
Dedicated DevOps Oversight | — | — | ✓
Quarterly Version Releases | — | — | ✓
Weekly Stakeholder Reports | — | — | ✓
PM Monthly Check-in | — | ✓ | ✓
Emergency SLA | — | — | 4 hours
Billing Model | Monthly or Annual | Monthly or Annual | Annual (upfront)
ANNUAL CONTRACT SUMMARY
Starter Care Annual | 8000 | Save $1,600 vs 12 months at monthly rate of $800
Pro Care Annual ★ | 15000 | Save $3,000 vs 12 months at monthly rate of $1,500
Enterprise Annual | 25000 | Save $5,000 vs 12 months at monthly rate of $2,500